|  |  |  |
| --- | --- | --- |
| Letter | Activity | Duration (Hours) |
| A | Discuss and Setup Lines of Communication | 1 |
| B | Create GitHub Repository | 0.5 |
| C | Organise Weekly Team Meeting | 0.5 |
| D | Complete Belbin Assessment | 1 |
| E | Assign Team Roles | 0.5 |
| F | Justify role allocation | 1 |
| G | Create Trello Board | 0.5 |
| H | Define Focus Questions | 2 |
| I | Create Initial Concept Map | 2 |
| J | Create Initial Ontology | 3 |
| K | Risk Analysis Table | 2 |
| L | Justify Risk Analysis Decisions | 2 |
| M | Create Gantt Chart | 5 |
| N | Create WBS Directory | 5 |
| O | Create WBS Tree Diagram | 2 |
| P | Discuss Critical Paths For Project | 0.5 |
| Q | Create Activity Network Diagram | 5 |
| R | Create PERT Chart | 4 |
| S | Discuss System Requirements | 1 |
| T | Create System Requirements List | 2 |
| U | Meet as a Team and Discuss | 1 |
| V | Discuss System Requirements | 1 |
| W | Develop system requirements Document | 2 |
| X | Discuss Development Methodologies + Justify them | 3 |
| Y | Create Use Case Diagram | 7 |
| Z | Create Story Board | 7 |
| AA | Create Class Diagram | 7 |
| BB | Create Domain Models | 7 |
| CC | Create Robustness Diagram | 7 |
| DD | Create Sequence Diagram | 7 |
| EE | Meet as a Team and Discuss | 1 |
| FF | Discuss Architecture Design | 2 |
| GG | Create Architecture Design | 5 |
| HH | Discuss User interface design | 2 |
| II | Create User Interface | 5 |
| JJ | Meet as a Team and Discuss | 1 |
| KK | Discuss and Document International Coding Standards | 1 |
| LL | Upload System Code to GitHub | 1 |
| MM | Divide Coding Tasks Between Members | 0.5 |
| NN | Work on coding project | 35 |
| OO | Discuss Development Progress | 1 |
| PP | Unit Testing Code | 7 |
| QQ | Create Test Plan + Document Results | 7 |
| RR | Meet as a Team and Discuss | 1 |
| SS | Discuss and divide Tasks | 1 |
| TT | Create User Guide | 14 |
| UU | Create Developer Guide | 14 |
| VV | Conclude Project with Team Discussion | 1 |
|  |  |  |

|  |  |
| --- | --- |
| Letter Can Happen If | These Letters are completed before |
| A | First Task |
| B | A |
| C | A |
| D | A |
| E | B, C, D |
| F | E |
| G | F |
| H | G |
| I | H |
| J | H |
| K | H |
| L | K |
| M | N |
| N | I, J ,K |
| O | N |
| P | M |
| Q | P |
| R | Q |
| S | O, R |
| T | S |
| U | T, L |
| V | U |
| W | V |
| X | V |
| Y | X, W |
| Z | Y |
| AA | Y |
| BB | AA, Z |
| CC | BB |
| DD | BB |
| EE | DD, CC |
| FF | EE |
| GG | FF |
| HH | GG |
| II | HH |
| JJ | II |
| KK | JJ |
| LL | KK |
| MM | LL |
| NN | MM |
| OO | NN |
| PP | OO |
| QQ | PP |
| RR | QQ |
| SS | RR |
| TT | SS |
| UU | SS |
| VV | TT, UU |

|  |  |
| --- | --- |
| Letter Can Happen If | These Letters are completed before |
| A | First Task |
| B |  |
| C |  |
| D |  |
| E |  |
| F |  |
| G |  |
| H |  |
| I |  |
| J |  |
| K |  |
| L |  |
| M |  |
| N |  |
| O |  |
| P |  |
| Q |  |
| R |  |
| S |  |
| T |  |
| U |  |
| V |  |
| W |  |
| X |  |
| Y |  |
| Z |  |
| AA |  |
| BB |  |
| CC |  |
| DD |  |
| EE |  |
| FF |  |
| GG |  |
| HH |  |
| II |  |
| JJ |  |
| KK |  |
| LL |  |
| MM |  |
| NN |  |
| OO |  |
| PP |  |
| QQ |  |
| RR |  |
| SS |  |
| TT |  |
| UU |  |
| VV |  |
| WW |  |